## Sheet1
Identity Stage |  |  |  | Analysis Stage |  |  |  | Plan Stage | Action Stage
ID | Date Created | Short Description | Description | Risk Category | Likelihood | Impact | Matrix (Priority) | Proposed Mitigation | Progress
[9 empty] | Status | Date | Likelihood | Impact | Matrix
1 | 2021-02-06 | Server host shuts down | The server shutting down will have an effect on the project depending in which sprint/position it is in | Completion rate | Low | Medium | Low | No mitigation | No down time occured during this project | 2021-02-24 | Low | Low | Low | Medium | Low | Medium | High
2 | 2021-02-06 | Database is attacked and data is breached | (SQL injection) Attackers may be able to read information from the database | User data | High | Low | Medium | Make sure project hides all sensitive information | MySQL username and password can be seen throughout the project files. This is low impact because no sensitive data is being stored and databases are down when not in use. | 2021-03-02 | High | Low | Medium
3 | 2021-02-06 | Illness, or other "Acts of God" | Something may cause the project to not be completed | Completion rate | Medium | High | High | Avoid doing anything that could cause me to be unable to work. Get as much work done as soon as possible | Nothing caused me to be unable to work. | 2021-03-07
4 | 2021-02-06 | Technical difficulities | Developer may find implementing a feature too difficult with current knowledge | Completion rate | Medium | Medium | Medium | Keep features within the specification of the training course so they are not too difficult to complete | Not all features ended up being implemented | 2021-02-24 | Medium | Medium | Medium